CENTREFIT GROUP

CRM Build Plan

Version 1.0

24 March 2026

Prepared by Sage

CONFIDENTIAL

# Table of Contents

# 1. Executive Summary

This document outlines a 26-week phased build plan for the Centrefit CRM, a unified platform designed to serve all three business units of Centrefit Group: Solutions, Communications, and Services. The CRM will replace the existing Tradify system with a purpose-built, mobile-first application that delivers consumer-grade polish for field operations, quoting, scheduling, finance, and reporting.

The platform is built on a modern stack comprising Next.js 16, TypeScript, Supabase (PostgreSQL, Auth, Storage, Real-time, Edge Functions), Tailwind CSS v4, and deployed on Vercel. Deep integration with Xero handles all accounting workflows. The build delivers 13 modules across 9 distinct phases, progressing from core foundations through to data migration and go-live.

The guiding philosophy is speed over features, mobile-first design, and zero training required for field technicians. Every screen must pass the two-tap test for common actions and meet Square/Uber-level design quality.

# 2. Architecture Overview

## Tech Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js 16 + React 19 + TypeScript | Server-rendered UI with App Router |
| Styling | Tailwind CSS v4 | Utility-first, dark mode default |
| Components | shadcn/ui | Accessible, customisable component library |
| Backend | Supabase PostgreSQL | Primary database with Row Level Security |
| Auth | Supabase Auth | JWT-based authentication with RBAC |
| Storage | Supabase Storage | File uploads (photos, receipts, documents) |
| Real-time | Supabase Realtime | Live updates for scheduler and dashboards |
| Edge Functions | Supabase Edge Functions | Server-side logic (Deno runtime) |
| Hosting | Vercel | Serverless deployment with preview branches |
| Accounting | Xero API | Two-way sync for invoices, payments, contacts |
| Email | Resend | Transactional emails (quotes, invoices, notifications) |
| PDF Generation | React-PDF | Quote PDFs, invoice PDFs, scope documents |

## Environments

| Environment | URL | Purpose |
| --- | --- | --- |
| Development | localhost:3000 | Local development and testing |
| Preview | *.vercel.app (per PR) | Automated preview deployments per pull request |
| Staging | staging.centrefit-crm.vercel.app | Pre-production testing and UAT |
| Production | crm.centrefit.com.au | Live production environment |

# 3. Design Principles (Non-Negotiable)

Every design decision, feature scope call, and UI implementation must adhere to the following principles. These are non-negotiable and take precedence over feature requests or timelines.

- Two taps or less for common field actions — If a technician needs more than two taps to start a timer, update a status, or log a note, the UX has failed.

- Consumer-grade polish — The quality bar is Square, Uber, and Linear. Not trade software. Not enterprise grey.

- Zero training required for techs — A new technician should be able to clock on, view their jobs, and update status without any training session.

- Mobile-first, not mobile-adapted — Design for the phone screen first. Desktop is the adaptation, not the other way around.

- Speed over features — Optimistic UI updates, offline-first data patterns, sub-200ms interactions. Cut features before cutting speed.

- Contextual simplicity — Show only what the user needs for their current task. Progressive disclosure for everything else.

- Dark mode default — The primary interface is dark. Light mode is secondary.

# 4. User Roles

| Role | User | Permissions |
| --- | --- | --- |
| Admin | Mitchell | Full system access. All CRUD, settings, user management, financial approvals, reporting, Xero config. |
| Finance Manager | Sue | Invoice generation, Xero sync management, AR/AP dashboards, credit notes, purchase orders, payment tracking, financial reporting. |
| Project Manager | Assigned per project | Job management, scheduling, quoting, staff assignment, contractor portal management, document generation. |
| Field Staff | Technicians | Mobile job view, time clock, photo capture, receipt scanning, job status updates. Read-only on financials. |

# 5. Build Phases

The build is organised into 9 sequential phases spanning 26 weeks. Each phase builds upon the previous and includes defined acceptance criteria that must be met before progressing.

| Phase | Name | Weeks | Key Deliverables |
| --- | --- | --- | --- |
| 1 | Foundation and Core | 1–4 | Auth, customers, jobs, design system |
| 2 | Scheduler and Staff | 5–6 | Calendar, staff management, assignments |
| 3 | Suppliers, Parts and Quoting | 7–9 | Supplier CRUD, parts catalogue, quote engine |
| 4 | Mobile PWA and Field Ops | 10–12 | PWA, time clock, photos, receipt scanner |
| 5 | Contractor Portal | 13 | Magic links, external contractor forms |
| 6 | Finance and Xero Integration | 14–18 | Invoicing, billing rates, Xero sync, P&L |
| 7 | Documents and Plan Builder | 19–21 | Plan builder, document gen, asset register |
| 8 | Sales Pipeline and Reporting | 22–24 | Pipeline kanban, reports, dashboards |
| 9 | Migration and Go-Live | 25–26 | Tradify migration, UAT, cutover |

## Phase 1: Foundation and Core

Timeline: Weeks 1–4

### Objectives

- Scaffold Next.js 16 + Supabase + Tailwind CSS v4 project structure

- Establish design system: dark mode default, component library (shadcn/ui), responsive breakpoints

- Implement authentication with Supabase Auth and role-based access control (4 roles)

- Build customer CRUD with sites and contacts management

- Build job CRUD with 5-phase state machine

- Create navigation shell and application layout

### Modules

- Auth and RBAC Module

- Customer Management Module

- Job Management Module

- Design System / Component Library

### Database Tables

- customers

- customer_contacts

- customer_sites

- jobs

- job_staff

- job_notes

- job_time

- staff

- categories

- statuses

- nbn_steps

### Key Screens

- Login / Registration

- Dashboard (shell)

- Customer List + Detail + Edit

- Site Management (per customer)

- Contact Management (per customer)

- Job List + Detail + Edit

- Job State Machine (Pre-Work → Quoting → In Progress → Tracking/Hold → Completion)

- Navigation sidebar / mobile nav

### API Endpoints

- /api/auth/* — Authentication endpoints

- /api/customers — CRUD

- /api/customers/:id/sites — Site management

- /api/customers/:id/contacts — Contact management

- /api/jobs — CRUD with state transitions

- /api/staff — Staff listing and profiles

### Acceptance Criteria

- Can create customers with multiple sites and contacts

- Can create jobs and assign them to customers/sites

- Job state transitions enforce valid flow through 5 phases

- Login works with all 4 roles and permissions are enforced

- Design system renders correctly in dark mode across mobile and desktop

### Dependencies

- None — this is the foundation phase

### Risks

- Supabase schema design must support all future phases to avoid costly migrations

- shadcn/ui component customisation for dark mode may require significant overrides

## Phase 2: Scheduler and Staff

Timeline: Weeks 5–6

### Objectives

- Build weekly and daily calendar views with drag-and-drop job assignment

- Implement staff management with availability, skills tracking, and billing rates

- Job-staff assignment with automatic conflict detection

### Modules

- Scheduler Module

- Staff Management Module

### Database Tables

- schedule_entries

- staff_availability

- billing_rates

### Key Screens

- Weekly Calendar View

- Daily Calendar View

- Staff List + Detail + Edit

- Staff Availability Matrix

- Drag-and-Drop Job Assignment

### API Endpoints

- /api/schedule — CRUD for schedule entries

- /api/schedule/conflicts — Conflict detection

- /api/staff/:id/availability — Availability management

- /api/staff/:id/billing-rates — Rate management

### Acceptance Criteria

- Can schedule jobs to staff on the calendar

- Drag-and-drop assigns staff to time slots

- Conflicts are visually highlighted and prevent double-booking

- Staff availability correctly blocks out unavailable periods

### Dependencies

- Phase 1 complete (jobs and staff tables exist)

### Risks

- Calendar performance with large numbers of concurrent jobs

- Drag-and-drop UX on mobile touch devices

## Phase 3: Suppliers, Parts and Quoting

Timeline: Weeks 7–9

### Objectives

- Build suppliers CRUD (migrate 529 suppliers from Tradify)

- Build parts catalogue with pricing, cost, and markup management

- Integrate Quote Engine with 283 products, dependency rules, BOM generation, and labour calculation

- Implement quote lifecycle (Draft → Sent → Accepted → Declined)

- Quote-to-Job conversion workflow

### Modules

- Supplier Module

- Parts Catalogue Module

- Quote Engine Module

### Database Tables

- suppliers

- parts

- quotes

- quote_line_items

- product_dependencies

### Key Screens

- Supplier List + Detail + Edit

- Parts Catalogue Browser

- Quote Builder (product selection, dependency resolution, BOM)

- Quote Preview / PDF Generation

- Quote Lifecycle Manager

- Quote-to-Job Conversion Screen

### API Endpoints

- /api/suppliers — CRUD

- /api/parts — CRUD with pricing

- /api/quotes — CRUD with lifecycle transitions

- /api/quotes/:id/line-items — Line item management

- /api/quotes/:id/convert — Convert to job

- /api/products/dependencies — Dependency resolution

### Acceptance Criteria

- Can create quotes with accurate pricing including BOM and labour

- Product dependencies auto-resolve (selecting product X adds required products Y and Z)

- Quote PDF generates with professional formatting

- Accepted quotes convert to jobs with all line items carried over

- 529 suppliers successfully migrated from Tradify

### Dependencies

- Phase 1 complete (customer and job tables)

- Tradify supplier data export available

### Risks

- Quote Engine complexity — 283 products with dependency rules is substantial

- Pricing accuracy — markup calculations must be verified against Tradify outputs

## Phase 4: Mobile PWA and Field Operations

Timeline: Weeks 10–12

### Objectives

- Implement Progressive Web App (manifest, service worker, offline support)

- Build mobile-optimised job view for field staff

- Time clock with tap-to-start/stop functionality

- Photo capture and upload (job site photos)

- Job status updates from the field

- Receipt Scanner: camera capture, optional job tag, email photo to Xero bills inbox

### Modules

- PWA Module

- Mobile Field Operations Module

- Receipt Scanner Module

### Database Tables

- receipts

### Key Screens

- Mobile Job Dashboard

- Job Detail (mobile-optimised)

- Time Clock (start/stop with single tap)

- Photo Capture + Gallery

- Receipt Scanner (camera → optional job tag → email to Xero)

- Offline Queue Indicator

### API Endpoints

- /api/time-entries — Clock on/off

- /api/jobs/:id/photos — Photo upload

- /api/jobs/:id/status — Status update from field

- /api/receipts — Receipt capture and processing

### Acceptance Criteria

- Field staff can clock on/off with a single tap

- Photos upload correctly and attach to the right job

- Job status can be updated while offline (syncs when back online)

- Receipt scanner captures image and emails to Xero bills inbox

- PWA installs on iOS and Android home screens

### Dependencies

- Phase 1 complete (jobs, staff)

- Xero bills inbox email address configured

### Risks

- iOS PWA limitations (no push notifications, limited background sync)

- Offline sync conflict resolution for simultaneous edits

- Camera API inconsistencies across mobile browsers

## Phase 5: Contractor Portal

Timeline: Week 13

### Objectives

- Magic link generation from the scheduler for external contractors

- External contractor submission form (tasks, photos, materials, time, sign-off)

- Submission data flows back into the parent job record

- Optional repeat contractor login for returning contractors

### Modules

- Contractor Portal Module

### Database Tables

- contractor_tokens

- contractor_submissions

### Key Screens

- Magic Link Generator (admin side)

- Contractor Landing Page (external)

- Contractor Work Form (tasks, photos, materials, time)

- Contractor Sign-off Screen

- Contractor Submission Review (admin side)

### API Endpoints

- /api/contractors/tokens — Generate magic links

- /api/contractors/submit — External submission endpoint

- /api/contractors/submissions — Review submissions

- /api/contractors/auth — Optional repeat login

### Acceptance Criteria

- Can generate a magic link from the scheduler and send to a contractor

- Contractor opens link on phone, fills out work details, uploads photos, and signs off

- Submitted data appears in the job record within the CRM

- Returning contractors can optionally create a login for faster access

### Dependencies

- Phase 2 complete (scheduler)

- Phase 4 complete (mobile patterns)

### Risks

- Security of magic links (expiry, single-use vs. reusable)

- Contractor UX must be even simpler than field staff (zero context)

## Phase 6: Finance and Xero Integration

Timeline: Weeks 14–18

### Objectives

- Build invoice generation from completed jobs

- Implement 6-tier billing rate hierarchy

- Invoice lifecycle with configurable approval thresholds

- Xero OAuth integration with two-way sync (invoices, payments, contacts, account codes)

- Credit notes, purchase orders, and three-way matching

- AR/AP dashboards for Finance Manager

- Job profitability P&L

- Business unit P&L (Solutions / Communications / Services)

### Modules

- Invoicing Module

- Billing Rate Engine

- Xero Integration Module

- Purchase Orders Module

- Financial Reporting Module

### Database Tables

- invoices

- invoice_line_items

- credit_notes

- purchase_orders

- po_line_items

- goods_receipts

- payments

- payment_allocations

- supplier_bills

- billing_rate_cards

- payment_terms

- overdue_rules

- approval_thresholds

- xero_sync_log

- financial_audit_log

- expense_categories

### Key Screens

- Invoice Builder + Preview

- Invoice Approval Queue

- Xero Sync Dashboard (status, errors, manual retry)

- AR Dashboard (outstanding invoices, ageing, overdue)

- AP Dashboard (bills, purchase orders, payments due)

- Credit Note Generator

- Purchase Order Builder

- Three-Way Match Screen (PO vs. receipt vs. bill)

- Job Profitability P&L

- Business Unit P&L (Solutions / Communications / Services)

### API Endpoints

- /api/invoices — CRUD with approval workflow

- /api/invoices/:id/approve — Approval endpoint

- /api/credit-notes — CRUD

- /api/purchase-orders — CRUD with matching

- /api/xero/auth — OAuth flow

- /api/xero/sync — Trigger manual sync

- /api/xero/webhooks — Receive Xero events

- /api/reports/job-profitability — Per-job P&L

- /api/reports/business-unit — BU-level P&L

- /api/billing-rates — 6-tier rate management

### Acceptance Criteria

- Sue can generate invoices from completed jobs with correct billing rates

- Invoices push to Xero and appear in the correct account

- Payments recorded in Xero sync back to CRM automatically

- 6-tier billing rate hierarchy resolves correctly (staff > job > customer > category > BU > default)

- Approval thresholds enforce review for invoices above configured amounts

- Three-way matching validates PO against goods receipt against supplier bill

- Job profitability report shows accurate margin per job

- Business unit P&L breaks down by Solutions, Communications, and Services

### Dependencies

- Phase 1–4 complete (jobs, staff, time entries)

- Xero API credentials and sandbox account configured

### Risks

- Xero API rate limits may require queuing and retry logic

- Two-way sync conflict resolution (which system is source of truth?)

- Billing rate hierarchy edge cases with overlapping rules

- Financial data integrity — any bug here impacts real money

## Phase 7: Documents and Plan Builder

Timeline: Weeks 19–21

### Objectives

- Integrate Plan Builder for device placement and cable run documentation

- Document generation (scope of works, plan sets) from within the CRM

- Asset Register per customer site for ongoing maintenance tracking

### Modules

- Plan Builder Module

- Document Generation Module

- Asset Register Module

### Database Tables

- assets

- documents

- plan_projects

### Key Screens

- Plan Builder Canvas (device placement, cable runs)

- Document Generator (scope of works template)

- Plan Set Viewer / Editor

- Asset Register (per customer site)

- Asset Detail + History

### API Endpoints

- /api/plans — CRUD for plan projects

- /api/documents — Generate and manage documents

- /api/assets — CRUD per customer site

- /api/assets/:id/history — Maintenance history

### Acceptance Criteria

- Can create device placement plans with cable run annotations

- Scope of works documents generate from job and plan data

- Asset register tracks all installed equipment per customer site

- Documents attach to jobs and are accessible from job detail view

### Dependencies

- Phase 1 complete (customers, sites, jobs)

### Risks

- Plan Builder canvas performance on large floor plans

- Document template complexity and customisation requirements

## Phase 8: Sales Pipeline and Reporting

Timeline: Weeks 22–24

### Objectives

- Sales pipeline kanban board (Lead → Contacted → Quoted → Negotiating → Won → Lost)

- Stale service reminders that automatically feed the sales pipeline

- Full reporting suite (revenue, margins, utilisation, job completion, quote conversion rates)

- Configurable dashboard widgets

### Modules

- Sales Pipeline Module

- Reporting Module

- Dashboard Module

### Database Tables

- pipeline_deals

- pipeline_stages

- reports

### Key Screens

- Pipeline Kanban Board (drag-and-drop)

- Deal Detail + Activity Timeline

- Stale Service Alert Manager

- Revenue Report

- Margin Analysis Report

- Staff Utilisation Report

- Job Completion Report

- Quote Conversion Report

- Dashboard Widget Configurator

### API Endpoints

- /api/pipeline — CRUD for deals

- /api/pipeline/stages — Stage management

- /api/reports/* — Report generation endpoints

- /api/dashboard/widgets — Widget configuration

### Acceptance Criteria

- Pipeline kanban supports drag-and-drop between stages

- Stale service rules generate pipeline leads automatically

- All reports render correctly with real data from previous phases

- Dashboard is configurable per user role

- Full visibility across the entire business from a single dashboard

### Dependencies

- Phase 1–7 complete (all operational data flowing)

### Risks

- Report performance with large datasets

- Dashboard widget flexibility vs. complexity tradeoff

## Phase 9: Migration and Go-Live

Timeline: Weeks 25–26

### Objectives

- Tradify data migration: 5,010 jobs, 668 customers, 529 suppliers, 7 templates, billing rates

- Migration scripts with validation, dry-run mode, and rollback capability

- UAT with Sue (finance flows), field staff (mobile operations), Mitchell (full system)

- Parallel run period (both systems active)

- Go-live cutover and Tradify decommission

### Modules

- Data Migration Module

- UAT Coordination

### Key Screens

- Migration Dashboard (progress, errors, validation)

- Data Mapping Configuration

- Validation Report Viewer

- Parallel Run Comparison Dashboard

### API Endpoints

- /api/migration/import — Trigger migration run

- /api/migration/validate — Run validation checks

- /api/migration/rollback — Rollback to pre-migration state

- /api/migration/status — Migration progress

### Acceptance Criteria

- All 5,010 jobs migrated with correct status, dates, and associations

- All 668 customers migrated with sites and contacts intact

- All 529 suppliers migrated with correct details

- Billing rates and templates migrate accurately

- Sue validates financial data matches Tradify records

- Field staff complete real jobs using CRM during parallel run

- Tradify switched off — CRM is the single source of truth

### Dependencies

- All phases 1–8 complete and tested

- Tradify data export in agreed format

- Go-live date agreed with all stakeholders

### Risks

- Data quality issues in Tradify export (duplicates, missing fields)

- Parallel run reveals feature gaps requiring hotfixes

- Staff resistance to new system during transition

- Go-live timing — avoid peak business periods

# 6. Testing Strategy

Quality assurance is embedded in every phase, not bolted on at the end. The testing strategy combines automated checks with human validation to ensure reliability at every level.

| Layer | Tool | Scope | Trigger |
| --- | --- | --- | --- |
| Unit Tests | Vitest | Individual functions, hooks, utilities, business logic | Every commit (pre-commit hook) |
| Integration Tests | Vitest + Supabase Test Helpers | API routes, database queries, auth flows, Xero sync | Every PR (CI pipeline) |
| E2E Tests | Playwright | Full user journeys across browser and mobile viewports | Every PR + nightly runs |
| UAT | Manual (structured scripts) | Business process validation with real users | End of each phase |

### Testing Requirements Per Phase

- Each phase must achieve minimum 80% unit test coverage on new code

- All API endpoints must have integration tests covering happy path and error cases

- E2E tests must cover the critical user journey defined in acceptance criteria

- UAT sign-off from the designated user (Sue for finance, field staff for mobile, Mitchell for admin)

- No phase is considered complete until all test suites pass in CI

# 7. Deployment Strategy

Deployments follow a progressive promotion model through environments, with automated checks at each gate.

| Stage | Environment | Trigger | Checks |
| --- | --- | --- | --- |
| Preview | Vercel Preview (per PR) | Every pull request | Build succeeds, E2E tests pass, visual diff |
| Staging | staging.centrefit-crm.vercel.app | Merge to main branch | Full test suite, database migrations verified |
| Production | crm.centrefit.com.au | Manual promotion from staging | Smoke tests, rollback plan confirmed |

### Rollback Procedure

- Vercel maintains the previous deployment as an instant rollback target

- Database migrations include down migrations for safe rollback

- Xero sync can be paused independently if integration issues arise

- Feature flags gate new functionality for progressive rollout

# 8. Data Migration Reference

This section documents the Tradify data export format, mapping rules, and validation requirements for the Phase 9 migration.

## Tradify Export Summary

| Entity | Count | Format | Notes |
| --- | --- | --- | --- |
| Jobs | 5,010 | CSV | Includes status, dates, assigned staff, customer reference |
| Customers | 668 | CSV | Includes sites and primary contacts |
| Suppliers | 529 | CSV | Contact details and payment terms |
| Templates | 7 | JSON | Quote and invoice templates |
| Billing Rates | Variable | CSV | Per-staff and per-category rates |

### Mapping Rules

- Tradify customer IDs map to CRM customer UUIDs via a lookup table

- Job statuses map to the 5-phase state machine (custom mapping per Tradify status)

- Supplier records map 1:1 with deduplication check on ABN/ACN

- Billing rates map to the 6-tier hierarchy (Tradify has a flat structure)

- All dates convert to UTC with AEST/AEDT awareness

### Validation Checks

- Row count validation: source count must match destination count per entity

- Referential integrity: all foreign keys resolve correctly post-migration

- Financial reconciliation: sum of invoice values in CRM matches Tradify totals

- Duplicate detection: flag and quarantine potential duplicates for manual review

- Data completeness: required fields populated, optional fields preserved where available

End of Document